## Instructions
Instructions
Background
Model changes often require changes in the dataset. Out of budget constraints we often have to implement an imperfect solution to align the ETLocal databases with the latest model version.
As a result, we risk misaligning our municipal dataset pipeline with all model changes since the last dataset update.
Purpose
This Excel file keeps track of deferred work to the municipal dataset pipeline. It documents the pipeline updates that have taken place and that should have been done, for future reference.
How do I use this document?
The tab 'Deferred work tracking' guides you through all relevant aspects of the municipal dataset pipeline. Use it as follows:
1. | Make a copy of the [New model change] column
2. | Fill all orange columns with the relevant data. Mostly these are symbols v / ! / ~ / x; see legend at the bottom of the page.
3. | Add clarifications in the optional grey fields.
Ask Koen van Bemmelen for help when in doubt.
Status updates
2025-11-24 | v1.0 of this deferred work tracking document created. The 'Quick fixes' in the Post-processing notebook still need to be created; not in use yet.

## Deferred work tracking
Pipeline Step | Description | Split Solar Full Load Hours | Update biogenic waste inputs | Rename gas power plant keys | [New model change]
| METADATA |  |  |  | [Copy this column to add a new model change]
Deploy tag |  | 2025.12 | 2025.12 | 2026-04
Deploy date |  | 2025-12-12 | 2025-12-12 | 2026-04-30
Date processed |  | 2025-11-21 | 2025-11-28 | 2026-05-07
Handled by |  | Kas Kranenburg & Koen van Bemmelen | Kas Kranenburg, Kyra de Haan & Koen van Bemmelen | Kyra de Haan
HELPER FUNCTIONS
| Alter or add functions or scripts in /src | n/a | n/a | n/a
(free text field for explanation)
INPUT COLLECTION
ETM Queries (NL dataset) | Update query dumps for new/changed keys | v | x | x
Other source files | Klimaatmonitor/CBS/etc if needed | v | n/a | n/a
| (free text field for explanation) | Updated query_dump_miscellaneous_input.txt Updated query_dump_2023_miscellaneous_output.txt | energy_distribution_biogenic_waste_energy_distribution_waste_mix_child_share --> input_percentage_of_biogenic_waste_energy_distribution_waste_mix energy_distribution_non_biogenic_waste_energy_distribution_waste_mix_child_share --> input_percentage_of_non_biogenic_waste_energy_distribution_waste_mix | energy_power_combined_cycle_network_gas_full_load_hours --> input_energy_power_combined_cycle_network_gas_full_load_hours energy_power_turbine_network_gas_full_load_hours --> input_energy_power_turbine_network_gas_full_load_hours
CALCULATION RULES & YAML
Calculation Rules (Excel) | Update ETLocal calculation rules | ! | x | x
YAML generation | Regenerate YAMLs from calculation rules | ! | x | !
| (free text field for explanation) | Calculation rules now use ground solar full load hours (950) for rooftop solar to leave data as-is. Calculation rules need to be updated to use correct flh. Regenerate yamls after updating rules | Checked: no ETLocal keys rely on this input. Updated YAML is necessary to fill the ETLocal template with data from the national dataset in the preprocessing notebook | YAMLs should be renamed for: - energy_power_combined_cycle_network_gas_full_load_hours - energy_power_turbine_network_gas_full_load_hours
EXTRACT & PREPROCESS
Extract & Preprocess notebook | Adjust KM/ETM/CBS data processing | v | n/a | v
| Update empty ETLocal template with new/changed ETLocal keys | v | x | x
| (free text field for explanation) | Adjusted national dataset querying and transformation Regenerated etlocal_template_empty_2025.csv | New keys need to be included in the ETLocal template | New keys need to be included in the ETLocal template
SECTOR NOTEBOOKS
Sector notebooks | Agriculture | n/a | n/a | n/a
| Area | n/a | n/a | n/a
| Buildings | n/a | n/a | n/a
| Built environment stock Dutch municipalities | n/a | n/a | n/a
| Energy production | n/a | n/a | n/a
| Households | n/a | n/a | n/a
| Industry | n/a | n/a | n/a
| Non energetic emissions | n/a | n/a | n/a
| Other energy demand | n/a | n/a | n/a
| Transport | n/a | n/a | n/a
| (free text field for explanation) | Notebooks might still show the diagrams based on the old yamls. Should be fixed upon re-running. | These inputs are not used in any of the sector notebooks | These inputs are not used in any of the sector notebooks
POST-PROCESSING
Post-processing notebook | Adjustments in template merging | n/a | n/a | n/a
| Alteration to data.csv and/or commits.yaml | ! | ! | !
| (free text field for explanation) | Only commits.yaml updated. Data.csv should be regenerated after running the Extract and preprocess source data notebook. | If the Extract and preprocess notebook is run, both data.csv and commits.yaml should be updated accordingly in this notebook. Running this notebook has not been done yet | If the Extract and preprocess notebook is run, both data.csv and commits.yaml should be updated accordingly in this notebook. Running this notebook has not been done yet
QUICK FIX (IN POST-PROCESSING NOTEBOOK)
Quick fix applied? | Retrospective correction on data.csv/commits.yaml | n/a | n/a | n/a
| (free text field for explanation) | n/a | n/a | n/a
AMALGAMATOR
Regional datasets | Update RES and provincial datasets | n/a | n/a | n/a
| (free text field for explanation) | Separate ETLocal data migration has been performed for this update | Separate ETLocal data migration has been performed for this update | Separate ETLocal data migration has been performed for this update
NOTES
Relevant context | Specify reasons or background for not implementing a thorough fix, if applicable | Using correct flh in pipeline results in dataset update for all municipalities, which was undesirable | Minor update. Postponed so that it can be bundled with future updates. | Minor update. Postponed so that it can be bundled with future updates.
Notes for thorough fix | Any specific considerations or things to watch out for, if applicable | n/a | n/a | n/a
Priority | High/Medium/Low for cleanup | Medium | Low | Low
Status | Open/In progress/Resolved | Open | Open | Open
LEGEND
v | Completely and thoroughly done
~ | Quick fix applied (see Quick fixes sections in Post-processing notebook)
! | Partially done / needs to be redone
x | Not done (deferred)
n/a | Not relevant for this change
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Requires clarification. What does this mean?